## ACL & History
Document Title
Version | Prepared by | Reviewed by | Approved by | Approval Date
<Current Version #> | <Prepared by: Name of the person who implemented the change> | <Name of Reviewer: Name of the person who reviewed the change.> | <Name of Approver: Name of the person who approved the change> | <MM/DD/YYYY>
Access List:
List of Users | Access Type | Type of Media | Retention Period
(Read, Write)
Read / Write
Read

## Sheet3
Batch | Functional Area | Module | Extension Type | Extension Name | Actual Build | Actual Build Review | Actual UT | Actual UT Review | Current Status
1 | Account Management | CAM | Apex Trigger | SCR_ CreateModifyContactAddressScreen _AT_3 |  | 0.5 | 0.5 | 0.5 | Completed
1 | Account Management | CAM | Apex Trigger | SCR_ CreateModifyContactAddressScreen _AT_4 |  | 0.5 | 0.5 | 0.5 | Completed
1 | Account Management | CAM | Apex Trigger | SCR_ CreateModifyContactAddressScreen _AT_5 |  | 0.5 | 0.5 | 0.5 | Completed
1 | Publication & Pricing Catalog | PC | Custom Object | Promotion Package | 0.5 |  |  |  | Completed
1 | Publication & Pricing Catalog | PC | UI Page | Promotion Package | 0.5 |  |  |  | Completed
1 | Publication & Pricing Catalog | PC | Validation Rule | SCR_ PackageCreation_VR_1 |  |  | 0.5 |  | Completed
1 | Publication & Pricing Catalog | PC | Validation Rule | SCR_ PackageCreation_VR_4 |  |  | 0.5 |  | Completed
1 | Publication & Pricing Catalog | PC | Validation Rule | SCR_ PackageCreation_VR_5 |  |  | 0.5 |  | Completed
1 | Publication & Pricing Catalog | PC | Custom Object | Eligible Rule Master / Promotion eligibility Rules |  |  | 0.5 |  | Completed
1 | Publication & Pricing Catalog | PC | UI Page | Eligible Rule Master / Promotion eligibility Rules |  |  | 0.5 |  | Completed
1 | Publication & Pricing Catalog | PC | Custom Object | Promotion Gift |  |  |  | 0.5 | Completed
1 | Publication & Pricing Catalog | PC | UI Page | Promotion Gift |  |  |  | 0.5 | Completed
1 | Publication & Pricing Catalog | PC | Custom Object | Package(Rework) |  |  |  | 0.5 | Completed
Total
Batch | Functional Area | Module | Extension Type | Extension Name | Actual Build | Actual Build Review | Actual UT | Actual UT Review | Current Status
1 | Publication & Pricing Catalog | PC | Custom Object | Promotion Package |  |  | 0.5 |  | Completed
1 | Publication & Pricing Catalog | PC | UI Page | Promotion Package |  |  | 0.5 |  | Completed
1 | Publication & Pricing Catalog | PC | Custom Object | Gift |  |  |  | 0.5 | Completed
1 | Publication & Pricing Catalog | PC | UI Page | Gift |  |  |  | 0.5 | Completed
1 | Publication & Pricing Catalog | PC | Custom Object | Promotion Gift |  | 0.5
1 | Publication & Pricing Catalog | PC | UI Page | Promotion Gift |  | 0.5
1 | Publication & Pricing Catalog | PC | Custom Object | Eligible Rule Master |  | 0.5
1 | Publication & Pricing Catalog | PC | UI Page | Eligible Rule Master |  | 0.5
1 | Account Management | VAM | Report | Vendor Allocation Report |  | 0.5
1 | Account Management | VAM | Report | SingPost Addresses Report (Post Sector Ops Rep Mapping object ) |  | 0.5
1 | Publication & Pricing Catalog | CAM | VF Page | VF Page on Account edit screen (SCR_AccountDetailScreen_CAR_1) |  | 0.5
1 | Publication & Pricing Catalog | PC
1 | Publication & Pricing Catalog | PC
1 | Publication & Pricing Catalog | PC | Validation Rule | SCR_ PackageCreation_VR_1 |  | 0.5
Batch | Functional Area | Module | Extension Type | Extension Name | Planned Start Date | Planned End Date
1 | Account Management | CAM | Apex Test Class | SCR_ CreateModifyContactAddressScreen _AT_3 | 2014-07-15 | 2014-07-16
1 | Account Management | CAM | Apex Test Class | SCR_ CreateModifyContactAddressScreen _AT_4 | 2014-07-15 | 2014-07-16
1 | Account Management | CAM | Apex Test Class | SCR_ CreateModifyContactAddressScreen _AT_5 | 2014-07-15 | 2014-07-16

## Sheet2
Batch | Functional Area | Module | Extension Type | Extension Name | Planned Start Date | Planned End Date
1 | Account Management | CAM | Page Layout | MailingAgentAccount_PL | 2014-07-10 | 2014-07-10
Batch | Functional Area | Module | Extension Type | Extension Name | Planned Start Date | Planned End Date
1 | Account Management | CAM | Apex Test Class | SCR_ CreateModifyContactAddressScreen _AT_3 | 2014-07-15 | 2014-07-16
1 | Account Management | CAM | Apex Test Class | SCR_ CreateModifyContactAddressScreen _AT_4 | 2014-07-15 | 2014-07-16
1 | Account Management | CAM | Apex Test Class | SCR_ CreateModifyContactAddressScreen _AT_5 | 2014-07-15 | 2014-07-16

## Sheet4
SCR_ CreateModifyContactAddressScreen _AT_3 | Populate Address Unique ID fields on Contact and Account based from the Address Unique ID of Address record | Before | Insert | Address Unique ID fields in Contact and Accounts will have a value of the Address Unique ID from Address record. This field will be used in global search. | Contact | Contact BL | Account
Update
SCR_ CreateModifyContactAddressScreen _AT_5 | Validate that only 1 Billing Contact is associated to Account | Before | Insert | If Billing Indicator is ticked, system will check if there is already a Billing Contact associated to Account. An error message will be displayed if there is an existing Billing Contact associated to the Account. | Contact | Contact BL | Account
Update
CAM | SCR_ CreateModifyContactAddressScreen _AT_4 | Validate Account Field Airline Indicator is ticked and Address Record Type is Airline | Before | Insert | System will check if Record Type of Address Object is Airline. If yes, system will check if the Account associated to the Contact record has Airline Indicator ticked. | Contact | Address BL | Account, Address | I believe this must be placed in Contact trigger since the transaction is in Contact object.
Update
Error message Invalid Address Record Type for Airline Account will be displayed if Address Record Type is not Airline.